## Sheet1
Project Title | Start Date
Factors that impact quality of life | 2022-11-28
Project Duration
7 Days
Questions | End Date
What are the factors that impact the quality of life? | 2022-12-02
Could quality of life factors vary from area to area?
| Task Name | Status | Start Date | Due Date | Estimated Duation | Actual Duration | Comments
Deliverables | Looking over excel datasets | Completed | 2022-11-28 | 2022-12-05 | 20 minutes | 10 minutes | Trying to make connections
Project Management Plan | Find another dataset | Completed | 2022-11-28 | 2022-12-05 | 1 hour | 3 hours | Ending up going back to find datasets after finding ones that werent the best to work with
Entity-Relationship Diagram (ERD) | Cleaning Data | Completed | 2022-11-28 | 2022-12-05 | 3 hours | 8 hours | Going back to edit stuff I missed, adding stuff back, new dataset
ETL Documentation | ERD | Completed | 2022-11-29 | 2022-12-05 | 3 hours | 3 hours | Editing and finalizing after input
SQL DDL Table Schema | DDL | Completed | 2022-11-29 | 2022-12-05 | 3 hours | 3 hours | Had some mishaps but ending up working through them + making dml
Napkin Drawings of Visualizations | ETL Documentation | Completed | 2022-11-29 | 2022-12-05 | 1 hour | 2 hours | Had to go back and add more details and new dataset
Document of Napkin Drawing of Visulatizations Feedback | Napkin Drawing | Completed | 2022-11-30 | 2022-12-05 | 1 hour | 30 minutes | after looking at data wasn't too bad to draw
Power BI Reports | Feedback | Completed | 2022-11-30 | 2022-12-05 | 30 minutes | 10 minutes | feedback was helpful
Project Report | Power BI Visualizations | Completed | 11/31/2022 | 2022-12-05 | 2 hours | 2 hours | A lot of playing around to see what made sense
| Excel Visualizations | Completed | 2022-12-02 | 2022-12-05 | 4 hours | 6 hours | A lot of trying to figure out what made sense and how to work with all of the datasets
| Report | Completed | 11/31/2022 | 2022-12-05 | 4 hours | 1 hour | Finally putting everything together